## Website
| 20th Jan |  |  |  |  | 27th Jan |  |  |  |  | 3rd Feb |  |  |  |  | 10th Feb |  |  |  |  | 17th Feb |  |  |  |  | 24th Feb
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Design MyPlanner & Homepage | bar: 20th Jan T to 20th Jan W
Rachael to review & feedback changes | bar: 20th Jan T
Amend if required and finalise design | bar: 20th Jan F
Build Homepage & MyPlanner | bar: 27th Jan M to 27th Jan F
Rachael to review test site & feedback | bar: 3rd Feb M to 3rd Feb F
Amend if required and finalise | bar: 10th Feb M to 10th Feb F
Design PDF Scrapbook | bar: 27th Jan M to 27th Jan T
Rachael to review & feedback changes | bar: 27th Jan W
Amend if required and finalise design | bar: 27th Jan T to 27th Jan F
Build PDF Scrapbook | bar: 3rd Feb M to 3rd Feb F
Rachael to review PDF output & feedback | bar: 10th Feb M to 10th Feb W
Amend if required & finalise | bar: 10th Feb T to 10th Feb F